## Checklist
Test Plan Review Checklist
Project: | Electronic E-commerce Shop Website
Release:
Reviewers
Document: | Test Plan
Date: | December 14, 2025
Document ID:
Template Used: | Test Plan Review Checklist.xls 1.0
No. | Criteria | Yes/No/NA | Remarks
A | OVERVIEW
1 | Does the test plan template conform to the specified standards/guidelines? | Yes | Tuân theo chuẩn IEEE 829 với đầy đủ: mục tiêu, phạm vi, chiến lược, tài nguyên, lịch trình
2 | Can the boundaries or scope of the test be clearly identified? | Yes | Phạm vi rõ ràng: 14 modules (Auth, Product, Cart, Order, Payment, Review, Wishlist, Notification, Admin, Security, Performance, Database, API, UI/UX)
3 | Are all prerequisites and other related documents identified? | Yes | Có đầy đủ: phân tích use case, schema DB, API documentation, kế hoạch triển khai
4 | Is the test traceable to requirement(s)? | Yes | Mỗi test case ánh xạ rõ ràng với UC1-UC4, đảm bảo truy vết từ yêu cầu đến kết quả
5 | Is the test plan under version control? | Yes | Sử dụng Git với chiến lược nhánh: main, uc1-4, feature, bugfix
B | CONTENT
1 | Does the Test Plan address the following required information clearly? | Yes | Tất cả phần được tài liệu hóa đầy đủ với cấu trúc rõ ràng
2 | Test Objectives | Yes | Kiểm thử chức năng (APIs, UI), hiệu năng (<3s), bảo mật (SQL injection, XSS), responsive design
3 | Test Scope | Yes | Frontend User/Admin, Backend API, MySQL DB, Momo Payment, Notification - 14 modules
4 | Test Strategy | Yes | 5 cấp: Unit (Jest-485 TCs), Integration, System, UAT, Regression tự động
5 | Resources (such as material, tools and human) | Yes | Jest v30.2.0, Supertest v7.1.4, Postman, MySQL Workbench, Docker, GitHub Actions
6 | Test Schedule | Yes | 6 tuần: Sprint 1-2 (Unit), Sprint 3-4 (Integration), Sprint 5-6 (System/UAT)
7 | Test Environment | Yes | 3 môi trường: Dev (localhost+Docker), Staging (Railway/Vercel), Production
8 | Test Deliverables | Yes | 485 test cases, 51 báo cáo lỗi, báo cáo tổng kết, coverage report (>80%)
9 | Test Reporting | Yes | Tổng kết thực thi (91.75% pass), theo dõi lỗi theo mức độ, coverage theo module
10 | Does the test plan identify the essential team member roles & responsibilities? | Yes | QA Lead (lập kế hoạch), Test Engineers (thực thi), Dev Team (sửa lỗi), Product Owner (phê duyệt)
11 | Does the plan include detailed specifications, descriptions, and procedures for testing all systems? | Yes | Chi tiết: điều kiện tiên quyết, các bước test, kết quả mong đợi cho từng test case
12 | Does the document describe the type(s) of tests to be addressed? | Yes | Unit, Integration, System, Performance, Security, API, UI/UX testing
13 | For the test type, does the document list all relevant tests necessary to be applied to the chosen part of the system? | Yes | 485 TCs: Auth (45), Product (62), Cart (38), Order (52), Payment (35), Review (28), Wishlist (22), Notification (30), Admin (58), Security (42), Performance (25), Integration (28), API (40), UI/UX (35)
14 | Are integration tests included? | Yes | End-to-end: Đăng nhập → Duyệt SP → Giỏ hàng → Thanh toán Momo → Xác nhận ĐH
15 | Is the test coverage sufficient? | Yes | Độ phủ 91.75% (445/485 pass). Unit tests phủ 7 modules: auth, cart, order, product, review, wishlist
16 | Is the schedule within a currently agreed time frame? | Yes | Chu kỳ 6 tuần phù hợp timeline, đủ thời gian cho tất cả cấp độ kiểm thử
17 | Are the testing dependencies (if any) addressed? | Yes | Đã xử lý: seed scripts, Momo sandbox credentials, Docker environment
18 | Has the entrance criteria for the testing activities been identified? | Yes | Modules deployed, môi trường sẵn sàng, test data loaded, test cases approved
19 | Has the exit criteria, including thresholds for performance deviation, for the testing activities been identified? Example: All severity 1 and 2 defects must be closed and approved plans for severity 3 defects are defined in the Test Report. | Yes | 100% TC thực thi, >90% pass, 0 critical bugs, <2 high bugs, hiệu năng <3s
20 | Has a regression strategy been defined for regression testing when changes or enhancements in system design occur? | Yes | Automated suite (Jest), chạy mỗi PR/merge, focus critical paths

## Doc Control
This information is for template control purpose only. This page can be removed when an actual document is made.
Document Control Page
Test Plan Review Checklist
Template version: | 1.1
Template status: | Approved
Template file name: | Test Plan Review Checklist.xls
Template document ID | CK-PP-091002
Revision history of this template
Version No. | Revision Date | Change Description | Author's Name | Approver's Name | Approver's Title
0.8 | 2009-09-25 | Draft | Duc, Chau Man
0.9 | 2009-12-09 | Reviewed, corrected | Du Chu
1.0 | 2010-01-04 | Approved |  | Hy Thai | DE Manager
1.02 | 2011-01-26 | Remove A1, B1, B2, B3, B4, B5, C12, C13, D1, D2, D3, D5, D6, D7, D8, D9, D12, D13, D14 Add C15 -> 19 (before removal) | Tien Tran
1.05 | 2011-02-14 | Add 2 checkpoints about entrance criteria and exit criteria based on OPAL Detailed Test Plan | Tien Tran
1.1 | 2011-02-15 | Approved | Tien Tran | Tien DD | SEPG Head
Usage notes:
Use this template to develop the various kinds of documents. The content of the document are subjected to be filled and changed in the document, according to the following legends:
Blue comment: The brief guidance on how to fill the sections. These parts shall be removed from the actual documents.
Example (Red text): The brief example to illustrate the sections. These parts shall be removed from the actual documents.
[Text in brackets]: Shall be replaced with the actual contents.